## Tracker
ID | Priority | Title | Required Change (summary) | Acceptance Criteria (summary) | Files/Areas | Status | Owner | PR Link | Evidence Path | Notes/Blockers
0.1 | P0 | Replace browser tokens with secure cookie sessions | Move OAuth to backend, issue HttpOnly+Secure+SameSite cookie; remove localStorage tokens; withCredentials on frontend | No localStorage tokens; cookie set with HttpOnly+Secure; API requires cookie; server-side logout clears cookie | frontend/src/apiClient.ts; frontend/src/pages/Login.tsx; frontend/src/services/googleCalendarService.ts; frontend/src/providers/GoogleAuthProvider.tsx; backend/app/api/api.py; backend/app/api/google_auth.py | Needs approval |  |  | evidence/A1-browser-tokens.md | Architecture change; requires approval before implementing
0.2 | P0 | Encrypt provider refresh tokens at rest | App-layer encryption (DEK/KMS) for provider tokens; add enc+iv columns; backfill; drop plaintext | Encrypted columns present; rotation documented; no raw tokens in logs | backend/app/models/user.py; backend/app/db/migrations/add_google_auth_fields.py; admin backfill+drop endpoints | In Progress |  |  | evidence/A2-token-encryption.md
0.3 | P0 | Remove or sanitize raw HTML rendering | Replace dangerouslySetInnerHTML with sanitizer (DOMPurify) or markdown | No direct dangerouslySetInnerHTML for user content; tests strip <script>/onerror | frontend/src/components/modules/EditableSection.tsx; frontend/src/pages/PublicBlog.tsx | Completed |  |  | evidence/A3-xss-sanitization.md
0.4 | P0 | Lock down uploads by size and type | Enforce MIME allowlist and 20MB cap; stream uploads; return 413/415 | 413 on >20MB; 415 on disallowed type; no full file load in memory | backend/app/api/chat.py; backend/app/api/legal.py; backend/app/services/document_processor.py | Completed |  |  | evidence/A4-upload-guards.md
0.5 | P0 | CORS and secret key hardening | Restrict prod origins; avoid allow_methods[*]; require non-default SECRET_KEY via env | Process exits in prod if SECRET_KEY/DATABASE_URL missing; allow_origins only official UI | backend/app/core/config.py; backend/app/main.py | Completed |  |  | evidence/A5-cors-secret.md
0.6 | P0 | Replace admin header token with RBAC | Remove X-Admin-Token; require authenticated session and admin role; add rate limiting/audit; IP allowlist/VPN | 401 without valid session+admin; no ADMIN_TASKS_TOKEN refs | backend/app/api/admin_tasks.py; auth middleware | Completed |  |  | evidence/A6-admin-rbac.md
A7 | P0 | Disable configuration probe endpoint in prod | Remove or restrict /api/test/config to internal/admin-only | Endpoint not available in prod; 403/404 externally | backend/app/api/test_config.py | Completed |  |  | evidence/A7-config-probe.md
A8 | P1 | Remove hardcoded Google Client ID fallback | Require VITE_GOOGLE_CLIENT_ID; fail build if missing; no literals in repo | No literal client IDs; build fails without env | frontend/src/providers/GoogleAuthProvider.tsx; frontend/src/pages/TestGoogleAuth.tsx | Completed |  |  | evidence/A8-google-client-id.md
1.1 | P1 | Brute force protection and admin 2FA | Rate limit /token per user/IP; enable WebAuthn/TOTP for admin | 10 wrong attempts/15m block; admin can enroll 2FA | backend/app/api/api.py; backend/app/api/superadmin.py; frontend admin UI | In Progress |  |  | evidence/P1-1.1-bruteforce-2fa.md
1.2 | P1 | RAG and AI safety guardrails | Pin system prompt; tool allowlist; source citations; tests against prompt injection | Exfiltration test fails; answers cite sources | backend/app/services/rag_chat.py; tests | Not started |  |  | evidence/P1-1.2-rag-guardrails.md
1.3 | P1 | Schema migrations via Alembic | Introduce Alembic; remove startup DDL; versioned scripts | alembic/versions populated; app starts without DDL | backend/app/db/migrations (new alembic); backend/app/db/db_init.py | Not started |  |  | evidence/P1-1.3-alembic.md
1.4 | P1 | Security headers and CSP at edge | Serve via proxy with CSP,HSTS,XCTO,Referrer-Policy; start report-only; enforce | Report-only zero violations; strict CSP enabled | Render/NGINX/edge config; backend/app/main.py headers added; frontend/public/index.html if meta used | Partial |  |  | evidence/P1-1.4-csp.md | App-level headers added; edge CSP pending
1.5 | P1 | Observability health and error reporting | /healthz /readyz; structured JSON logs with request IDs; Sentry | Probes <50ms; errors captured with IDs; redactions applied | backend/app/main.py; logging config; Sentry setup | Completed |  |  | evidence/P1-1.5-observability.md
2.1 | P2 | PII masking and selective encryption | Identify sensitive fields; mask in logs/admin; encrypt targeted columns | Sensitive fields masked; policy/lint checks present | backend logging; admin UIs; schemas | In Progress |  |  | evidence/P2-2.1-pii-masking.md
2.2 | P2 | Dependency and image scanning in CI | Add SAST/dependency/container scans; publish SBOM; fail on high CVEs | CI fails on high CVEs; SBOM attached | .github/workflows; backend/requirements.txt; frontend/package.json; Dockerfiles | In Progress |  |  | evidence/P2-2.2-ci-scanning.md
2.3 | P2 | Docker hardening | Multi-stage builds; run as non-root; minimal images | Non-root USER; smaller image; Trivy shows no high CVEs | backend/Dockerfile; frontend/Dockerfile | Completed |  |  | evidence/P2-2.3-docker-hardening.md